## SLOC
Team Number: | 9
Week: | 1
Program Size (SLOC) | Actual
Base | 0 | Current SLOC:
Added | 0 | Physical : 0
Deleted | 0 | Source : 0
Modified | 0 | Comment : 0
Reused | 0 | Files : 0
From COTS | 0
Total New SLOC | 0

## COTS
List of third-party components being considered for use in the system as of 10/09/2019
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
React Native | Frontend framework for the system | N/A | Node.js |  | x
Firebase | Store user information | N/A | Node.js |  | x
Node.js | Javascript for building backend service | N/A | Firebase |  | x
Food API (provided by client) | Source for images of food to be displayed, to receive user preferences (ie. if he has tried that food item or not) | N/A | Node.js, Firebase | x
Social media login APIs | Allow user login into the app via social media accounts namely, Facebook, Instagram and Google | N/A | Firebase, Node.js |  | x
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References
N/A | N/A |  | N/A

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Learn how to use React Native to build frontend mobile applications
2 | Learn how to use NodeJS to build the backend for React Native
3 | Generate win-win conditions
4 | Explore and investigate database options(Firebase, MySQL, etc)
5
6
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | Win-win conditions (must be generated this week in order to be finalized on Tuesday 9/22)
2
3
4
5
C. | List your accomplishments from the previous week
1 | Client Interaction Report
2 | Better understanding of the kind of app we are to build, and with what features
3 | Identified stakeholders, beneficiaries, cost associated with the project
4 | Came up with a few win-win conditions
5
6
7
8