## Risk
Top Project Risks as of 09/18/2020
Rank |  | Risk Description | What causes this risk? | Risk Mitigation Action Items | P(L) 1-10 | S(L) 1-10 | RE | Rationale why the risk exposure has changed? | No. of Weeks Active
This Week | Last Week
1 |  | Issues can arise due to lack of developer knowledge regarding React Native on how to implement an app | Lack of developer knowledge | Learn and research about React Native and build prototypes (Buying Information, Risk Mitigation) | 4 | 6 | 24 | N/A | 1
2 |  | Compatibility of the database with the remaning tech stack | Lack of experience using the database with the tech stack to be used | Learn and research if it is possible to use the database(MySQL or Firebase) with React Native, Node.JS and build prototypes(Buying Information, Risk Mitigation) | 2 | 7 | 14 | N/A | 1
3 |  | Issue can arise with adding the 'login via social media accounts' feature in the app | Lack of experience with integrating APIs during login | Learn about API integration and implement at least one login via social media functionality | 2 | 4 | 8 | N/A | 1
4 |  | Integration of MyFitnessPal API which provides us the food dataset with the product | Lack of experience integrating this API or lack of documentation available for integration of this API | Read through the documentation of the API | 3 | 5 | 15 | N/A | 1
5 |  | Issue with collaboration amongst teammates | Schedules of each team members are different | Have weekly zoom calls with the team, communicate via slack and actively help each other | 5 | 4 | 20 | N/A | 1
6 |  | Integration issue of the frontend and backend for login and signup functionality | Difference in tech stacks being used such as React Native, NodeJS and Firebase | Gain proper knowledge about individual technologies, so that the team knows how to integrate functionalities. | 4 | 8 | 32 | N/A | 1
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0

## Defects, Problems and Concerns
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | Lack of developer knowledge about building mobile appliations using React Native | Learn and research about building mobile applications using React Native.
2
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | The team members debated the use of Android Studio vs. React Native for the implementation | The team members explored both technologies and chose the one which could be expanded more to the iOS platform.
2 | The team members debated the various types of social media logins to be included in the mobile application. | Waiting for confirmation from client about the same.
3 | The team members debated the use of Firebase vs. MySQL for the databases | The team members are in the process of exploring both alternatives.
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | N/A | N/A
2
3
4
5