## SLOC
Team Number: | 9
Week: | 3
Program Size (SLOC) | Actual
Base | 0 | Current SLOC:
Added | 455 | Physical : 0
Deleted | 0 | Source : 0
Modified | 0 | Comment : 0
Reused | 0 | Files : 0
From COTS | 0
Total New SLOC | 0

## COTS
List of third-party components being considered for use in the system as of 10/09/2019
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
React Native | Frontend framework for the system | N/A | Firebase |  | x
Firebase | Store user information | N/A | React Native |  | x
Food API (provided by client) | Source for images of food to be displayed, to receive user preferences (ie. if he has tried that food item or not) | N/A | React Native, Firebase | x
Social media login APIs | Allow user login into the app via social media accounts namely, Facebook, Instagram and Google | N/A | Firebase, Firebase |  | x
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References
Node.js | The team did a research on the technologies that needed to be used. We have decided to not use Node.js, and develop the app just by using React Native and Firebase database to build backendless applications. |  | https://blog.jscrambler.com/integrating-firebase-with-react-native/ and other tutorials that use React Native and Firebase for app development

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Research about the mechanism to store images in products database
2 | Complete integration of login and signup
3 | Research about the Food API to be used
4 | Start implementation of the swiping feature
5 | Design frontend for the swiping feature
6
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | The client will confirm the API to be used (MyFitnessPal or USDA API or Nutritionix)
2 | The database to be used in the initial phase does not contain images, we are waiting to hear from the client how to integrate the images and which images to use
3
4
5
C. | List your accomplishments from the previous week
1 | Better understanding of the kind of app we are to build, and with what features
2 | Began implementation of login and sign up feature, completed the front-end
3 | Setup Firebase account and database
4 | Created dummy database to use for initial development purpose
5
6
7
8