## Risk
Top Project Risks as of 09/18/2020
Rank |  | Risk Description | What causes this risk? | Risk Mitigation Action Items | P(L) 1-10 | S(L) 1-10 | RE | Rationale why the risk exposure has changed? | No. of Weeks Active
This Week | Last Week
1 |  | Issues can arise due to lack of developer knowledge regarding React Native on how to implement an app | Lack of developer knowledge | Learn and research about React Native and build prototypes (Buying Information, Risk Mitigation) | 2 | 6 | 12 | The team has performed research about React Native and has built a basic login and signup functionality. So the team feels more confident about the tech stack. | 3
2 |  | Compatibility of the database with the remaning tech stack | Lack of experience using the database with the tech stack to be used | Learn and research if it is possible to use the database(MySQL or Firebase) with React Native, Node.JS and build prototypes(Buying Information, Risk Mitigation) | 1 | 7 | 7 | Considering all the alternatives, the team has finalized to move ahead with using Firebase as the database. We have also implemented the signup and login features using Firebase. | 3
3 |  | Issue can arise with adding the 'login via social media accounts' feature in the app | Lack of experience with integrating APIs during login | Learn about API integration and implement at least one login via social media functionality | 2 | 4 | 8 | N/A | 3
4 |  | Integration of food data API which provides us the food dataset with the product | Lack of experience integrating this API or lack of documentation available for integration of this API. Multiple alternatives are presented by the client which needs more in-depth knowledge to narrow down on a single API. | Read through the documentation of the API | 3 | 6 | 18 | We have received new food API alternatives from the client in our most recent meeting on September 29 | 3
5 |  | Issue with collaboration amongst teammates | Schedules of each team members are different | Have weekly zoom calls with the team, communicate via slack and actively help each other | 2 | 4 | 8 | We have been having scheduled meeting and followups for tasks and debugging sessions. | 3
6 |  | Integration issue of the frontend and backend for login and signup functionality | Difference in tech stacks being used such as React Native, NodeJS and Firebase | Gain proper knowledge about individual technologies, so that the team knows how to integrate functionalities. | 0 | 8 | 0 | We have modified our architecture to remove the nodeJS intermediate layer between ReactJS frontend and Firebase database. The architecture would now only have integration of ReactNative with Firebase, which the develope team is familiar with. | 2
7 |  | Storing of product images and profile pictures in the Firebase Database | Lack of knowledge on how to store large amount of image files in the Firebase database | Gain more knowledge on Cloud Firestore | 5 | 8 | 40 | N/A | 1
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0

## Defects, Problems and Concerns
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | Lack of developer knowledge about building mobile appliations using React Native | Learn and research about building mobile applications using React Native.
2 | Lack of clarity on the business workflow of the application | Had frequent client meetings and interactions to come up with a reasonable workflow. The top risk prototype also helped in getting this clarity.
3 | Lack of understanding of the requirements of the prototype presentation | Change the approach to identifying the most risky feature in the project and then build a prototype, instead of doing the other way round.
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Need for a nodeJS middleware for the system architecture | The team performed reasearch and came to a common understanding that Firebase can be directly integrated with React Native to build backendless applications.
2
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | N/A | N/A
2
3
4
5